## MINUTES OF BATCH MEETING

February 24, 2002      2:00pm

QC Science High School Alumni Room

Present :  Bobbie and Des Fuerte , Resie Singuio , Manny Rapadas , Rico Pagulayan ,

Ana Marie Fondevilla , Mike Marqueda , Dr Vic Corpuz , Emel Duque

Elmo Martinez

### Committee Update

I. Program   -   reported by Elmo

Program proper – 2 parts ( Business and Fellowship )

Stage / Backdrop – to be handled by batch ‘92

Registration – c/o Vic  ( to prepare handtags )

Invitations – c/o Resie , Lilibeth ( draft of letter by March

-messages from GMA , VP Guingona , City Mayor , Principal

Sound System / Lights – P 4,000.00

Program – to prepare batch presentation

Security – c/o Roel Calinisan / Rico ( Bgy Tanod / Students to act as marshals /                                	      usherettes /  P 200 token for them )

Parking – to prepare parking tickets

Total Budget of committee – P 8,800.00

II. Food  committee – reported by Mike

Prepare for 400 pax

Menu : Cocktails ( Canapes , Pasta , Hot and cold , Dessert )

Beverage :  Wine ( white and red ) , Champagne

Mineral water to be provided by Manny Rapadas .

Budget :	Food ( 400 X P 240 )		P 96,000.00

Beverage                                    19,000.00

Total Budget of Committee      -	          P 115,000.00 ( plus 10%

contingency  for price increase )

#### III . Souvenier – Reported by Des

#### Marble paperweight to be donated by Ana Marie .

PR campaign – advertorial design c/o Des and Kinjo / P 200 / copy for

souvenier program plus CD

Explore other ideas for souvenier item .

Total Budget of Committee – P 80,000.00  ( 400 X P200 )

IV .  Finance Committee – Chaired by Manny Rapadas

Target Funds :

Sponsorship		P 100,000.00

Pledges ( abroad )	    50,000.00

Pledges ( local )	    50,000.00

Ticket Sales 	               300,000.00  ( 1,000 X P 300 / ticket )

Other fund-raising activities : co-sponsor a concert bingo socials

Other Matters :

Kick-off ceremony / Family Day – April 20 , 2002 /  8AM / QC Science

( Bingo / Raffle ) / Collection of pledges / Presentation of Sept 07 program

Batch Nominee for Achievement Award – Lilibeth Deapera

Next Meeting : March 24, 2002 / Manny Rapadas’ house  / 2pm .